## Slide 1: Enhancing Your Section 508 Assessment: A Project Management Framework for Greater Efficiency
Project Management for the Section 508 Annual Assessment: A Structured Approach
Frederick Harris, PMP
Division Chief, User Interface and Metrics
frederick.t.harris11.civ@mail.mil
DoD – Defense Technical Information Center (DTIC)
May 21-22, 2025
Notes: Good morning and thank you for joining.
I’m Frederick Harris, but I go by Fred. I serve as the Division Chief for User Interface and Metrics at the Defense Technical Information Center, often abbreviate DTIC.
I’m a certified Project Management Professional (PMP). The Section 508 program, including the annual assessment process, is part of my division’s oversight.
I want to start by recognizing the depth of experience and profound commitment many of you bring to accessibility compliance. The goal of this session is to offer a project-oriented perspective that can help organize and sustain efforts like the Section 508 Annual Assessment.
My focus today is not on the content of the assessment itself, but on how project management principles can support the planning, coordination, and delivery of that work more efficiently and predictably.
We’ll explore how structured framing, including defined roles, timelines, and workflows, can help strengthen what many of you are already doing, especially as agencies work toward more repeatable and scalable Section 508 submission processes.

## Slide 2: Disclaimer
The views and opinions expressed are those of the speaker and do not reflect the official policy or position of the Defense Technical Information Center (DTIC), the Department of Defense, or the U.S. Government.
Notes: Before we dive in, let me clarify that the views and opinions I’m sharing today are my own.
They don’t represent the official position of the Defense Technical Information Center, the Department of Defense, or the U.S. Government.
That said, everything I’m going to walk you through is informed by practical experience, established best practices, and guidance from recognized authorities like the Project Management Institute, the GAO, and other federal accessibility initiatives.
My aim is to offer a structured lens that helps make the Section 508 assessment more manageable and repeatable.

## Slide 3: Agenda
What the Section 508 Annual Assessment Is
Why a Project-Based Approach Helps
Project Management Phases in Practice
Tools, Techniques, and Real-World Tactics
Challenges and solutions
Key takeaways and Q&A
Notes: Here’s a quick look at where we’re going in this session.
I’ll start by grounding us in what the Section 508 Annual Assessment is and why it matters, then introduce a project management lens — not as a replacement, but as a way to strengthen what many of you are already doing.
We’ll walk through the five key project phases — and I’ll note here that PMI formally refers to these as process groups. But for clarity and flow, I’ll be presenting them as distinct phases, just to help structure the conversation more intuitively.
Then we’ll look at some practical tools and templates, and close with real-world takeaways you can adapt to your own agency’s process.
I’ll leave time at the end for Q&A, but feel free to jot down questions as we go.

## Slide 4: Project Management 101 Overview
Project Lifecycle
What is a project
Triple Constraints: Scope – Time – Cost
The impact of changing a single constraint
Initiate
Plan
Iterative Execution
Monitor
Close
Notes: Before we get into the specifics of how project management applies to the Section 508 assessment, I want to take a moment to ground us in some foundational concepts.
Many of you may already be familiar with project management principles, but for our purposes today, I’m going to highlight just a few that are especially relevant.
First, we define a project as a temporary effort undertaken to create a unique product, service, or result. That’s important — because the Section 508 assessment, although recurring, is a distinct effort with a defined beginning and end, a set of required outputs, and cross-functional coordination. In other words, it behaves like a project.
The project lifecycle is typically divided into five process groups: Initiate, Plan, Execute, Monitor, and Close. You’ll see that these phases mirror the natural rhythm of a well-managed assessment cycle — from defining scope and timelines to tracking progress and submitting results.
One of the core ideas I want to introduce here is the concept of the triple constraint — scope, time, and cost. If you adjust one, it impacts the others. For example, if the due date is fixed and scope expands — perhaps your agency is required to report on more domains than in the past — then effort and resource requirements naturally increase. Understanding that interdependence helps us set realistic expectations and make smarter trade-offs during the planning and execution phases.
We’re not aiming to turn the Section 508 program into a rigid project office — but introducing just enough structure to make the process repeatable, trackable, and less stressful for everyone involved

## Slide 5: What is the Section 508 Assessment?
Required annually by GSA and OMB
Evaluates accessibility maturity across programs
Covers key capability areas such as program management, acquisition, testing, remediation, and training
Due for submission by July-August
Supports agency-wide accessibility improvement initiatives
Notes: Let’s take a moment to establish what the Section 508 Annual Assessment actually is — and just as importantly, what it isn’t.
Section 508 of the Rehabilitation Act of 1973 requires that all federal electronic and information and communication technology — or ICT — be accessible to people with disabilities. That includes both federal employees and members of the public who interact with government systems and services. The annual assessment is a way for agencies to report how they’re meeting that mandate.
At its core, the assessment is a governmentwide reporting requirement issued by GSA and OMB. It’s due every July and designed to help agencies evaluate their accessibility maturity across five domains: program management, acquisition, testing, remediation, and training.
This isn’t just a check-the-box exercise. Agencies are asked to assess their level of implementation in each area using four response options: Fully Implemented, Partially Implemented, In the Planning Stage, or Not Implemented. Depending on your agency’s structure and the year’s guidance, the assessment may include between 80 and 100 questions.
It’s comprehensive — and it’s not something a single office can complete in isolation. Input is often needed from policy teams, IT, procurement, legal, training — sometimes a dozen stakeholders or more. That kind of coordination is what makes the assessment a natural fit for a project-based approach.
Now, I’m not here to walk through every question or interpret policy guidance — GSA and your internal accessibility teams are your best resources for that. Instead, what I want to do is help you think differently about how the work gets done — and how we can bring more structure, consistency, and predictability to the process.
*** Extra Context ***
--- FY24: 103 the assessment framework is structured around 11 dimensions, which are grouped under two primary indices: the Maturity Index (m-index) and the Conformance Index (c-index).
I. Maturity Index (m-index): 9 Dimensions: These dimensions assess the organizational structures and processes that support digital accessibility:
  IT Accessibility Program Office
  Policies, Procedures, and Standards
  Communications
  Content Creation
  Human Capital, Culture, and Leadership
  Technology Lifecycle Activities
  Testing and Validation
  Acquisition and Procurement
  Training
II. Conformance Index (c-index): 1 Dimension
  This dimension measures the actual compliance outcomes of ICT products and services:
  Conformance Metrics
III. General Information: 1 Dimension
  This dimension provides contextual information about the reporting entity's Section 508 program:
  General Information

## Slide 6: Why Treat It as a Project?
Fixed annual deadline (July-August)
Multiple contributors and stakeholders
Complex data collections efforts across divisions
Need for clear roles and repeatable process
Risk of errors without structured
Coordination break downs without defined ownership
Notes: Now that we’ve established what the assessment is and why it matters, let’s talk about the central question of this session — why treat it as a project?
First, consider the characteristics of the annual Section 508 assessment. It has a fixed deadline. It requires input from multiple contributors across several functional areas. It involves structured reporting and coordination. Those are all hallmarks of a project.
Approaching it informally — without defined roles, a clear timeline, or planning tools — can make coordination more difficult and the workload harder to manage. That’s not a reflection of effort or intent — it’s a function of the process design.
What a project-based model offers is structure. With even lightweight project management principles in place — identifying roles early, setting milestones, monitoring progress — the assessment process becomes easier to navigate. It becomes something you can plan for, track, and sustain with more consistency.
The goal is to make the process more repeatable, manageable, and predictable, year after year.

## Slide 7: PM Framework – Initiate Phase
Define scope and objectives
Identify major milestones
Appoint contributors and clarify roles
Build a RACI Matrix
Secure leadership endorsements
Notes: This is where it all starts — and how you begin matters.
The Initiate phase is about setting a clear foundation. First, define the scope and objectives. What exactly are you trying to accomplish with this year’s assessment? What’s in scope — and just as importantly, what’s not?
Next, identify key milestones. These give your schedule structure and help you work backward from the July–August deadline.
You’ll also want to clarify who’s involved. Identify your contributors and be specific about their roles. This is where a RACI Matrix can really help — it makes responsibilities visible and prevents duplication or missed inputs later on.
Finally, secure leadership endorsement. Whether that’s your Section 508 coordinator, a senior manager, or your CIO — getting visible support up front gives the effort weight and helps eliminate confusion down the line.
The goal of this phase isn’t to plan every detail — it’s to establish intent, alignment, and commitment.

## Slide 8: PM Framework – Plan Phase
Develop a Work Breakdown Structure (WBS)
Build a project schedule (Gantt chart or timeline)
Assign tasks, owners, and deadlines
Establish communication cycles
Identify potential risks early
Notes: Once your scope is defined and your contributors are identified, you move into the Plan phase — and this is where structure really starts to take shape.
The planning phase is about breaking down the work into manageable pieces. One of the simplest and most effective ways to do that is with a Work Breakdown Structure, or WBS. It allows you to decompose the effort into smaller, actionable tasks — things like confirming data sources, coordinating policy inputs, testing ICT components, or drafting narrative responses. This becomes your blueprint for execution.
From there, build a schedule. You don’t need to be a certified project manager or expert scheduler — you just need to map out when things need to happen based on the July–August deadline. That can take the form of a Gantt chart, a calendar, or even a simple table in Excel. What matters is that it’s shared, visible, and reflects dependencies — so people know what has to happen first, what’s on the critical path, and where the pressure points are.
Next, assign owners. Every task needs a name next to it. Not a group, not an office — a person. That doesn’t mean they do all the work themselves, but they’re responsible for seeing it through. This helps prevent things from falling through the cracks.
You’ll also want to establish a rhythm of communication. That might be biweekly check-ins, milestone reviews, or status emails — whatever fits your culture. The important thing is that contributors know when they’ll be asked for updates and where to raise concerns early.
And finally, planning is the phase where you can start identifying risks. For example, is there a contributor who’s stretched thin? Are you relying on data from a system that tends to lag? Flag those early. Risk management doesn’t have to be complicated — just intentional.
This phase is where you lay the foundation for execution. It’s what gives the assessment process shape and predictability, instead of depending on memory or individual heroics to get across the finish line.

## Slide 9: PM Framework – Execution Phase
Collect data and validate inputs
Track work progress using project tools
Conduct accessibility testing sprints
Update stakeholders regularly
Manage emerging issues proactively
Notes: In this phase, contributors are completing their assigned tasks — gathering policy language, running accessibility tests, verifying training records, and reviewing procurement documentation.
The goal isn’t just to get the work done, but to execute against the schedule you created — in a way that’s coordinated, visible, and trackable.
One of the most helpful things you can do at this stage is give your team simple tools to track their own progress. That could be a shared checklist in Excel, a Planner board in Microsoft 365, or a shared workspace in SharePoint or Teams. When everyone can see where things stand, it reduces the need for someone to chase updates and helps keep momentum moving forward.
It’s also important to build in time for quality checks. Make sure your testing data aligns with what’s being reported. Confirm that acquisition language actually maps to accessibility standards. Even a quick review loop can catch inconsistencies early — when they’re easier to fix.
Another tactic that works well here is what I call testing sprints. Set aside focused windows of time — a few days, maybe a week — to run automated or manual accessibility scans. You don’t have to boil the ocean. But by making space for targeted evaluation, you uncover issues early enough to act on them and strengthen your reporting.
Finally, keep your stakeholders in the loop. Whether that’s a program sponsor, your Section 508 coordinator, or someone in your policy shop — regular updates help ensure no one is surprised by the timeline, the content, or the status of the submission.
The Execution phase is where effort meets organization. It’s where structure pays off — because instead of chasing status, you’re guiding a coordinated, time-bound set of activities toward a clear delivery point.

## Slide 10: PM Framework – Monitor Phase
Review progress against milestones
Track completion of assigned tasks
Update the risk register regularly
Monitor accessibility test results
Adjust schedules or plans as needed
Notes: As execution moves forward, we shift into the Monitor phase — and this runs in parallel. Monitoring isn’t something that happens after the work is done — it’s something that happens while the work is happening.
In this phase, your job is to keep track of progress against the schedule. Are contributors meeting their deadlines? Are tasks moving forward or getting stuck? Monitoring helps you spot issues early so you can adjust before they become blockers.
One of the most practical ways to do this is through milestone check-ins. These don’t have to be formal. A weekly or biweekly meeting, even a simple status report, helps you gauge what’s on track, what needs help, and where you might need to shift resources.
You’ll also want to revisit your risk register — even if it’s informal. Have any of the risks you identified during planning materialized? For example, has someone gone on unexpected leave? Did a data source take longer to access than anticipated? Monitoring those issues gives you a chance to reallocate or escalate early.
This is also a good time to monitor the quality and consistency of what’s being reported. For example, do the accessibility test results support the ratings being marked as 'Fully Implemented' or 'Partially Implemented’?
If one office reports mature training processes but another shows little to no staff participation, those discrepancies should be reconciled.
What you’re looking for is alignment across all domains — a consistent, accurate story about your agency’s accessibility posture.
That coherence strengthens the integrity of your submission and reduces the chance of needing last-minute corrections.
And keep in mind, not all updates have to be top-down. Encourage contributors to flag risks and delays proactively. Give them a clear way to raise their hand when they hit a snag — and reinforce that that’s part of a mature, responsive process.
Monitoring isn’t about micromanaging. It’s about maintaining momentum, anticipating issues, and making sure that the good work being done doesn’t get lost in silence or drift off schedule

## Slide 11: PM Framework – Close Phase
Conduct final review and quality checks
Secure leadership approvals
Submit the completed assessment
Archive documentation and working files
Capture lessons learned for future cycles
Notes: The final phase is Close — and while it may be the shortest, it’s where you lock in the value of all the work that came before it.
First, this is where you conduct a final review of your submission. You’re checking for completeness, coherence, and conformance with any formatting or delivery requirements set by GSA.
That includes making sure the official submission template was used — typically a spreadsheet or structured form provided through Section508.gov.
You’ll want to verify that all required fields are completed, dropdowns are selected appropriately, and that narrative responses fall within any stated character limits. GSA may also specify how the file should be named, who it should be submitted to, and how to confirm that submission was received.
It’s worth reviewing those details carefully — because even small formatting errors can trigger delays or clarification requests that slow down the process.
Once the review is complete, you’ll need to secure whatever approvals your agency requires. That might include a Section 508 Program Manager, a Chief Information Officer, or another designated authority. Getting those signatures lined up early helps ensure you’re not held up at the finish line.
Then comes submission — and once that’s done, a lot of people are tempted to move on immediately. But this is actually the perfect time to pause and reflect. If you’ve managed this effort as a project, you’ll have documentation — meeting notes, work plans, feedback, issues that came up — and all of that can be used to improve the process next year.
I encourage teams to archive their project documentation in a shared location and conduct a short lessons-learned session. What worked well? What should be done differently next time? Even capturing just a few insights can make a major difference when you restart the cycle.
The Close phase reinforces the idea that accessibility isn’t just an annual event — it’s a continuous effort. And the more we treat these processes as structured, repeatable, and learnable, the more resilient and mature our programs become over time."

## Slide 12: Tools and Templates
Use a RACI matrix to clarify roles
Build a Work Breakdown Structure (WBS)
Track deadlines using Planner, Excel, SharePoint
Document testing results with accessibility evaluation tools (ANDI, Microsoft Accessibility Insights for Web)
Manage files and communications in shared project
  space (Teams, SharePoint, JIRA, Confluence)
Notes: Let’s talk about tools and templates — not for the sake of adding complexity, but because having the right tools in place can make this entire process smoother, more predictable, and far less stressful.
First, a RACI matrix is one of the simplest ways to bring clarity to who’s doing what. It helps define who is Responsible, who is Accountable, who needs to be Consulted, and who simply needs to be Informed for each major task. You can build one in Excel, and once it’s shared, it eliminates a lot of confusion about who owns what.
Next is the Work Breakdown Structure — or WBS. This is your master list of tasks broken into logical categories, often aligned with the five domains of the assessment: program management, acquisition, testing, remediation, and training. A WBS provides structure without being rigid, and it gives contributors a clear view of how their piece fits into the whole.
To track deadlines and progress, most teams already have access to tools like Microsoft Planner, Excel, or even SharePoint task lists. These can serve as lightweight project management tools. You don’t need a full-blown project management suite — just something that helps people see what’s due, what’s done, and what’s still pending.
When it comes to documenting testing, tools like ANDI or Microsoft Accessibility Insights for Web can help run scans and capture evaluation results. The output from those tools — screenshots, reports, notes — can all be bundled into your internal documentation as evidence of testing efforts.
And then there’s your collaboration platform — whether it’s Microsoft Teams, SharePoint, JIRA, Confluence, or another system. Use these platforms to create a central workspace where files, status updates, meeting notes, and communications can live in one place. The easier it is for people to access and stay aligned, the more momentum your project will have.
The key here isn’t to overwhelm contributors with tools. It’s to give them the right support so that information flows, responsibilities are clear, and no one is carrying the entire process alone.

## Slide 13: Workflow Automation Tools for 508
Tool | Project Mgt. Role | Example Use
Microsoft Excel | Data Collection, Tracking, Reporting | Standardize response, track completion, auto-generate
Microsoft Teams / Outlook / Planner | Communications & Notifications | Status meetings, chat, updates, automated reminders
SharePoint | Document Mgt. | Store VPATs, automate approvals using Power Automate
JIRA | Task Tracking & Issue Mgt. | Log finding, assign owners, track resolution
Confluence | Documentation & Knowledge Sharing | Host process documentation, link JIRA tickets
Power Automate + Power Apps | Workflow Automation | Trigger document routing, alert
Power BI | Data Collection & Tracking, Visualization | Generate dashboards to monitor compliance trends
Notes: This slide represents a composite view — not of any specific agency, but of common dynamics that can emerge when complex, cross-functional work isn’t supported by a structured approach.
In the absence of clear roles and responsibilities, coordination can be inconsistent. Contributors may be unsure when to engage, what’s expected of them, or how their input fits into the larger process. That uncertainty can lead to delays or duplicate efforts — not out of neglect, but out of ambiguity.
Without a shared schedule or progress-tracking mechanism, it becomes harder to maintain momentum. Work might still get done — but status updates rely heavily on memory, email threads, or one person manually pulling everything together.
And when teams are managing deadlines without a formal plan, they’re less equipped to adapt to disruptions — whether that’s a shift in leadership priorities, staff availability, or unexpected gaps in information.
Again, this isn’t about pointing fingers — it’s about recognizing that the absence of structure creates friction, even in highly committed environments. And when we rely solely on informal coordination, we make success harder to sustain.
That’s what makes a project-based model so powerful: it doesn’t replace expertise — it supports it. And on the next slide, I’ll show what that support can look like in practice.

## Slide 14: Before – PM Implementation
Unclear contributor roles
Late or incomplete data submissions
Manual updates and coordination
High risk of missed deadlines
Problems discovered too late to address cleanly
Notes: Now let’s look at the other side of the picture — what the assessment process can look like when project management principles are applied in a practical, lightweight way.
First, there’s clarity. Roles are defined, contributors understand what’s expected of them, and tasks are assigned with accountability in mind. People don’t have to guess who owns what — and that reduces both delays and confusion.
There’s also a shared timeline — not just the final submission deadline, but milestones mapped backward so contributors know when drafts are due, when reviews happen, and when approvals need to be secured. That visibility makes it easier for teams to coordinate their efforts and plan around other priorities.
The tools being used aren’t just there for show — they serve a specific purpose. A RACI matrix helps clarify who’s doing what. A shared tracker — whether it’s in Excel, Planner, or another format — makes progress visible without anyone having to ask. Even a simple meeting cadence keeps communication flowing without overloading inboxes.
It’s not about the sophistication of the tools — it’s about how they help people stay aligned, stay informed, and stay on track.
Risk becomes something that’s actively managed instead of reacted to. If someone is out unexpectedly, or a policy review gets delayed, there’s a mechanism in place to adjust without derailing the overall timeline.
And most importantly — teams finish the cycle with documentation, insights, and momentum. They’re not reinventing the wheel next year, because they’ve already created a process they can refine, reuse, and build on.
Again, this isn’t about formality for formality’s sake. It’s about giving people structure that supports their work — not replaces it — and creates conditions for consistent, sustainable success.

## Slide 15: Key Takeaways
Treat the 508 assessment as a project
Use hybrid Waterfall + Agile approach when it fits
Leverage standard PM tools and templates
Engage stakeholders early
Enable proactive risk and issue management
Notes: As we begin to wrap up, I want to pause and highlight a few key takeaways from everything we’ve covered.
First — the Section 508 Annual Assessment is more than just a compliance exercise. It has all the characteristics of a project: a fixed timeline, defined outputs, and multiple contributors working toward a common goal.
Second — by applying project management principles, we’re not changing what the assessment asks for. We’re changing how we organize the work behind it. That means introducing structure in a way that supports contributors, increases consistency, and reduces the burden on any one person or office.
Third — structure doesn’t have to be heavy. Simple tools like timelines, task lists, shared workspaces, and role definitions can go a long way toward making the process smoother and more repeatable.
And finally — this is not about perfection. It’s about progress. Every time you apply a little more structure, you make the next cycle easier, more predictable, and more resilient.
So whether you’re starting fresh or looking to improve what you already have, my hope is that today’s session has offered a few practical ideas that you can take back and make your

## Slide 16: Next Steps
Assess your Section 508 processes and situation
Apply project management strategies to future accessibility efforts
Explore project management training opportunities
Leverage available templates and tools
Connect with accessibility and PM communities to stay supported and current
Notes: Thank you for staying with me through this walkthrough.
We’ve covered a lot — from the structure of the Section 508 Annual Assessment, to how project management principles can help coordinate and strengthen that process, all the way through to practical tools, templates, and real-world considerations.
I want to leave you with this: structure is not the opposite of flexibility. In fact, structure is what allows us to be more flexible — because we know where things stand, what’s coming next, and who we can count on.
The project lens doesn’t add red tape — it reduces ambiguity. It gives us something we can learn from and improve upon, year after year.
I know you are already doing meaningful, often invisible work to ensure accessibility is part of your agency’s culture.
What I’ve offered today is simply one way to support and scale that effort — to give it a framework that strengthens the quality of the work, and supports the people doing it.
With that, I’d love to open it up for questions — whether they’re about the framework, specific challenges you’re facing, or how to take the first step toward a more structured approach.

## Slide 17: Thank You and Q&A
Q & A
Notes: Thank you for your interest in this topic and for joining the session. I hope it gave you something useful to think about — and I’d be happy to take your questions.
We’ve covered a lot — from the structure of the Section 508 Annual Assessment, to how project management principles can help coordinate and strengthen that process, all the way through practical tools, templates, and real-world considerations.
I want to leave you with this: structure is not the opposite of flexibility. In fact, structure is what enables flexibility — because it tells us where things stand, what’s coming next, and who we can count on.
A project lens doesn’t add red tape — it reduces ambiguity. It gives us something we can learn from and improve upon, year after year.
I know many of you are already doing meaningful, often invisible work to embed accessibility into your agency’s culture. What I’ve shared today is simply one way to support and scale that work — by giving it a framework that strengthens both the quality of the process and the people behind it.
With that, I’d love to open it up for questions — whether they’re about the framework, the practical tools, or how to take that first step toward a more structured approach.

## Slide 18: Backup & Reference
Notes: This slide marks the end of the main presentation. The slides that follow are appendices, included for reference and discussion if needed during Q&A

## Slide 19: Appendix A – Sample RACI Matrix
Task | PM | UI Lead | IT Acqus. | Testing Team | Train Coord. | EX Spons.
Define scope and objectives | A | R | C | I | I | I
Identify major milestones | R | C | C | I | I | A
Appoint contributors and clarify roles | A | R | I | I | C | I
Build the RACI matrix | R | C | I | I | I | A
Secure leadership endorsement | I | I | I | I | I | A
Collect data and validate inputs | I | I | C | R | I | I
Conduct accessibility testing sprints | I | I | I | A/R | I | I
Notes: This is an example of how you might structure a simple RACI matrix for the assessment. It doesn’t have to be complex — the goal is to bring clarity to roles.
Who’s responsible for collecting data? Who needs to approve it? Who just needs to be informed? Having this defined early reduces confusion and helps prevent last-minute coordination issues.
*** Extra Information*** --- Ways to Enhance RACI Matrix:
-- Consider adding columns for: Due Date, Status (e.g., Not Started, In Progress, Complete), and Notes to track progress or exceptions.
-- This allows the RACI to double as a lightweight project tracker when more formal tools aren’t available.

## Slide 20: Appendix B – Example Gantt Chart
Phase | TASK | Duration (Weeks) | Start Date | End Date
Initiate | Kickoff Meeting | 1 | Wk 1 | Wk 1
Initiate | Assign 508 Roles / Define Compliance Scope | 1 | Wk 1 | Wk 2
Plan | Review Accessibility Requirements | 1 | Wk1 | Wk 2
Plan | Inventory Digital Assets | 2 | Wk 2 | Wk 4
Plan | Define Standards and Milestone | 1 | Wk 3 | Wk 4
Iterative Execute | Manual Testing (e.g., keyboard, ANDI) | 2 | Wk 4 | Wk 6
Iterative Execute | Compile Accessibility Gap Report | 1 | Wk 6 | Wk 7
Notes: This is a basic Gantt chart view structured using backward planning from the submission deadline. Key milestones may include policy review, content development, testing, internal approvals, and final packaging.
The goal isn’t to manage tasks by the hour, but to provide visibility and maintain steady progress at a manageable pace.
*** Extra Information*** --- Ways to Enhance Gantt Chart:
-- Additional fields could include: Start Date, End Date, Duration, Dependencies, % Complete, and Status indicators.
-- These columns can provide clearer visibility into progress, dependencies, and potential bottlenecks.

## Slide 21: Appendix C – 508 Risk Register
Risk | Likelihood | Impact | Owner | Mitigation Strategy
Delayed stakeholder input | High | High | Project Manager | Begin outreach early and schedule recurring syncs.
Inaccessible documentation | Medium | High | Content Owner | Review and remediate PDFs/forms early in the cycle.
Vendor noncompliance with 508 | Medium | High | Contracting Officer | Include 508 compliance language in contracts.
Missed deadlines | High | Medium | All Contributors | Use a shared timeline, send reminders
Notes: This example shows how a basic risk register can be used during the assessment cycle. Each risk entry can track potential obstacles — such as staffing gaps, delayed inputs, or technology issues — before they impact your timeline.
A simple spreadsheet like this can help teams identify and address potential problems before they escalate.
The goal isn’t to predict everything, but to build a habit of proactive thinking.
Even a lightweight risk register like this can help teams flag issues early and respond proactively.
*** Extra Information*** --- Ways to Enhance Risk Register:
-- Expand the risk register with columns like: Likelihood, Impact, Risk Level (combined score), Mitigation Strategy, Status, and Contingency Plan this additional information can help prioritize response efforts and give leadership early visibility.
-- This turns the register into a living tool that helps teams monitor and respond to evolving risks.

## Slide 22: Appendix D – Tools References
ANDI, Microsoft Accessibility Insights
M365 Tools (Planner, Teams, Excel)
JIRA, Confluence
Section508.gov
GSA 508 Assessment Template
Notes: This appendix highlights several tools that were mentioned earlier in the session — from accessibility testing platforms like ANDI and Microsoft Accessibility Insights for Web, to coordination tools such as Planner, SharePoint, and Teams.
These examples reflect commonly used options across agencies, but they’re by no means the only ones available. The intent is to provide a sample set that can be tailored to your environment

## Slide 23: Appendix E – Policy & Compliance
Section 508 of the Rehabilitation Act
OMB M-17-06 (Federal Government)
GSA Accessibility Conformance Reporting (ACR)
DoD CIO (if applicable)
GSA’s maturity model
Notes: This slide includes foundational references tied to the Section 508 Annual Assessment — including Section 508 itself, relevant OMB memoranda, and GSA’s maturity model.
It’s intended as a helpful reference point, not a complete catalog. Agencies may have additional internal directives or supplemental policy guidance that also shape their assessment approach."

## Slide 24: Appendix F – Lessons Learned
Start early
Automate where possible
Don’t wait until July to remediate
Start coordination early with division SMEs
Assign a single point of contact per division
Create reusable templates for intake and tracking
Use version control for shared documents
Keep a running risk register through the year
Notes: These are practical insights based on real-world implementation — like starting earlier, clarifying points of contact, and maintaining documentation for reuse.
It’s not a definitive checklist, but a collection of tactics that have made a measurable difference for teams managing the assessment over time. Use what fits, and build on it