## Slide 1: Streamline Your Annual Assessment
Frederick Harris, PMP
Division Chief, User Interface and Metrics
DoD – Defense Technical Information Center
May 21, 2025
Bringing Discipline to Accessibility: A Project Management Approach to Section 508

## Slide 2: Disclaimer
The views and opinions expressed are those of the speaker and do not reflect the official policy or position of the Defense Technical Information Center (DTIC), the Department of Defense, or the U.S. Government.

## Slide 3: Agenda
What is the Section 508 Annual Assessment?
Why treat it as a project?
Project management framework for the assessment
Tools and techniques
Challenges and solutions
Before-and-after project management transformation
Key takeaways
Q&A

## Slide 4: Project Management 101 Overview
Project Lifecycle
What is a project?
Triple Constraints: Scope – Time – Cost
The impact of changing a single constraint
Initiate
Plan
Iterative Execute
Monitor
Close

## Slide 5: What is the Section 508 Assessment?
Required annually by GSA and OMB
Evaluates accessibility maturity across programs
Covers program management, acquisition, testing, remediation, and training
Due for submission by July
Supports agency-wide accessibility improvements efforts

## Slide 6: Why Treat It as a Project?
Fixed annual deadline (July)
Multiple contributors and stakeholders
Complex data collections across divisions
Need for clear roles and repeatable process
Risk of errors without structured management

## Slide 7: PM Framework – Initiate Phase
Define scope and objectives
Identify major milestones
Appoint contributors and clarify roles
Build a RACI Matrix
Secure leadership endorsements

## Slide 8: PM Framework – Plan Phase
Develop a Work Breakdown Structure (WBS)
Build a project schedule (Gantt chart or timeline)
Assign tasks, owners, and deadlines
Establish communication cycles
Identify potential risks early

## Slide 9: PM Framework – Execute Phase
Collect data and validate inputs
Track work progress using project tools
Conduct accessibility testing sprints
Update stakeholders regularly
Manage emerging issues proactively

## Slide 10: PM Framework – Monitor Phase
Review progress against milestones
Track completion of assigned tasks
Update the risk register regularly
Monitor accessibility test results
Adjust schedules or plans as needed

## Slide 11: PM Framework – Close Phase
Conduct final review and quality checks
Secure leadership approvals
Submit the completed assessment
Archive project documentation and artifacts
Capture lessons learned for future cycles

## Slide 12: Tools and Templates
Use a RACI matrix to clarify roles
Build a Work Breakdown Structure (WBS)
Track tasks and deadlines with M365 Apps:
  Planner, Excel, SharePoint
Document testing results with accessibility evaluation tools (ANDI, Microsoft Accessibility Insights for Web)
Manage files and communications in shared project
  space (Teams, SharePoint, JIRA, Confluence)

## Slide 13: Before – PM Implementation
Unclear contributor roles
Late or incomplete data submissions
Manual follow-ups and tracking
High risk of missed deadlines
Reactive problem-solving

## Slide 14: Key Takeaways
Treat the 508 assessment as a project
Adopt hybrid Waterfall + Agile PM approach
Leverage standard PM tools and templates
Engage stakeholders early
Enable proactive risk and issue management

## Slide 15: Next Steps
Assess your Section 508 processes and situation
Apply PM principles to future accessibility initiatives
Explore project management training opportunities
Leverage available templates and tools
Engage with accessibility and PM communities

## Slide 16: Thank You! Q&A

## Slide 17: Backup & Reference

## Slide 18: Appendix A – Sample RACI Matrix
Task | PM | UI Lead | IT Acqus. | Testing Team | Train Coord. | EX Spons.
Define scope and objectives | A | R | C | I | I | I
Identify major milestones | R | C | C | I | I | A
Appoint contributors and clarify roles | A | R | I | I | C | I
Build the RACI matrix | R | C | I | I | I | A
Secure leadership endorsement | I | I | I | I | I | A
Collect data and validate inputs | I | I | C | R | I | I
Conduct accessibility testing sprints | I | I | I | A/R | I | I

## Slide 19: Appendix B – Example Gantt Chart
Phase | TASK | Duration (Weeks) | Start Date | End Date
Initiate | Kickoff Meeting | 1 | Wk 1 | Wk 1
 | Assign 508 Roles / Define Compliance Scope | 1 | Wk 1 | Wk 2
Plan | Review Accessibility Requirements | 1 | Wk1 | Wk 2
 | Inventory Digital Assets | 2 | Wk 2 | Wk 4
 | Define Standards and Milestone | 1 | Wk 3 | Wk 4
Iterative Execute | Manual Testing (e.g., keyboard, ANDI) | 2 | Wk 4 | Wk 6
 | Compile Accessibility Gap Report | 1 | Wk 6 | Wk 7

## Slide 20: Appendix C – 508 Risk Register
Risk | Likelihood | Impact | Owner | Mitigation Strategy
Delayed stakeholder input | High | High | Project Manager | Begin outreach early and schedule recurring syncs.
Inaccessible documentation | Medium | High | Content Owner | Review and remediate PDFS/forms early in the cycle.
Vendor noncompliance with 508 | Medium | High | Contracting Officer | Include 508 compliance language in contracts.
Missed deadlines | High | Medium | All Contributors | Use a shared timeline, send reminders

## Slide 21: Appendix D – Tools References
ANDI, Microsoft Accessibility Insights
M365 Tools (Planner, Teams, Excel)
JIRA, Confluence
Section508.gov
GSA 508 Assessment Template

## Slide 22: Appendix E – Policy & Compliance
Section 508 of the Rehabilitation Act
OMB M-17-06 (Federal Government)
GSA Accessibility Conformance Reporting (ACR)
DoD CIO (if applicable)
GSA’s maturity model

## Slide 23: Appendix F – Lessons Learned
Start outreach early with SMEs
Automate where possible
Don’t wait until July to remediate
Start coordination early with division SMEs
Assign a single point of contact per division
Create reusable templates for intake and tracking
Use version control for shared documents
Keep a running risk register through the year